## Risk Register
Risk ID | Asset | Vulnerability | Threat | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Control Recommendation | Control Type | Framework Mapping | Risk Owner | Status | Target Remediation Date | Notes
R-001 | Azure VM | Public RDP Exposure | Brute-force attack | 5 | 4 | 20 | Critical | Restrict RDP to IP / VPN | Preventive | ISO 27001 A.9.4 / CIS 12.3 | IT Security | Open
R-002 | Admin Account | No MFA | Credential compromise | 4 | 5 | 20 | Critical | Enable MFA & separate admin accounts | Preventive | ISO 27001 A.9.2 / NIST IA-2 | IT Security | Open
R-003 | Operating System | Default Configuration | Exploit known vulnerabilities | 3 | 4 | 12 | High | Apply CIS hardening & patching | Corrective | NIST CM-6 / CIS 5 | IT Ops | Open
R-004 | Logs | No SIEM | Undetected malicious activity | 3 | 3 | 9 | Medium | Enable centralized logging | Detective | ISO 27001 A.12.4 / NIST AU-2 | Security Team | Open
R-005 | Azure Account | Excessive Privileges | Unauthorized changes | 2 | 4 | 8 | Medium | Implement RBAC & least privilege | Preventive | ISO 27001 A.6.1 / NIST AC-6 | Cloud Admin | Open